## Clin Doc
Workstream: |  | Approved Decision | ICC Decision / Discussion | id (Hide column
Direction Setting Meeting: Clinical Discharge
1 | Physicians, Social Workers and PAs/Advanced Practice RNs will be able to document and update the patient's expected discharge date. Include Med Students and Residents and Midwives. | Approved by group |  | 73
2 | Physicians will update the problem list at discharge. Include nurse practitioners, Physician assistants, Med students and residents, include Midwives | Approved by group |  | 76
3 | What roles will be involved in the med reconciliation process? Physician, not PA, Nurse practitioners but not Advanced practice nurses. Also add Midwives | Approved by group |  | 77
4 | Physicians will use discharge Order Sets to place their discharge orders and patient instructions. | Approved by group |  | 78
5 | Physicians can enter the disposition in the discharge order, or unit clerks can enter it at discharge. Add admitting. At RVH the Rn calls admitting to them the time and d/c disposition of patient. | Approved by group |  | 79
6 | Nurses will document the removal of lines, drains, and airways in the Discharge Navigator. | Approved by group |  | 81
7 | Nurses and all other ancillary clinicians will use the shared Patient Instructions navigator section. | Approved by group |  | 83
8 | Nurses will print a copy of the After Visit Summary (AVS) and review the AVS with the patient | Approved by group |  | 84
9 | The discharge date, time, and disposition will be required to complete the discharge | Approved by group |  | 86
10 | Both nurses and unit clerks will have the security to discharge the patient when the patient leaves the facility. Add admitting | Approved by group |  | 87
11 | Any active inpatient orders will auto-discontinue 2 hours after patient is clinically discharged. | Approved by group |  | 88
12 | Nursing will have edit-access to chart for 7 days following the discharge via the discharged system list. | Approved by group |  | 90
13 | Physicians will use a standardized order set to discharge to outside facility | Approved by group |  | 91
14 | Social Workers or Discharge Planners will use discharge placement activity to plan and confirm a facility to send patients to when discharging to another facility | Approved by group |  | 92
15 | Discharged patient charts will be accessed via discharged patient lists | Approved by group |  | 93
16 | Physicians and mid-levels will have edit-access to a patientâ€™s chart for 30 days following discharge | Approved by group |  | 95
17 | We will use fax integration to communicate to external facilities that cannot receive/access electronic records post-discharge. | Approved by group |  | 96
18 | Deceased patients will be discharged with a disposition of expired.Selecting this disposition enables the Additional Deceased Information window. | Approved by group |  | 98
19 | The nurse will be able to fill out all discharge as deceased information, including the date and time of death as reported by the physician? | Approved by group |  | 100
20 | Users with security to discharge patients as deceased will be required to enter information in the Additional Deceased Information window. | Approved by group |  | 101
21 | Physicians will document the preliminary cause of death as discrete documentation in the Cause of Death navigator section | Approved by group |  | 102
22 | The system will automatically cancel any future appointments and other contacts when a patient is discharged as deceased. | Approved by group |  | 103
Direction Setting Meeting: Therapy Workflow
1 | Who will schedule outpatient therapy appointments? Department schedulers? Yes Should therapists be able to schedule their own appointments (have security for SnapBoard?)? Yes - Clerks, RN & Therapists | Approved by group |  | 119
2 | Inpatient Therapists will document goals using the Care Plan activity Therapist will need more information to make it work. Would like a Side Bar Print Group to be able to see the assessment and the flowsheet as the note is being built. If they can see their assessment in a side bar while they are documenting against the goals then they agreed this would work. EPIC thinks this functionality is possible, | Approved by group |  | 120
3 | Will therapist round on inpatients? no Will SLPs and Dieticians? no Will a therapy manager make assignments or will therapists assign themselves to patients? No - At HGH meet with therapist and give assignments. - At RVH divided between number of hours. No assignment. - At TOH and HI a therapist is assigned by unit (usually) - RVH and other small hospital will be a hospital list as well as TRC - TOH will be unit list | Approved by group |  | 121
Direction Setting Meeting: Clinical Discharge
1 | Nurses, nursing students, respiratory therapists, RT students, advanced practice nurses, and radiology technicians are the only roles who will have edit access to the MAR. All other users will have a read-only Summary MAR report. Current Process: When an MD gives a medication, they document the administration in their progress/procedure notes. The nurse would write on the MAR that the med was "given by MD, see notes" or something to that effect. EPIC recommended process: In EPIC, this would be accomplished using the "other provider" feature in the MAR. Discussion: There were comments in the room that is might be "against nursing college standards" to document for another despite the fact that if the RN does not put some note in the MAR then we wouldn't know if the patient got the med without having to read all the MD notes. This is not referring to emergency situations where there is scribe or in a specialty area like the OR. EPIC does not recommend that MD's have access to the MAR and do recommend we use the "other provider" function for these situations but the people in the room could not agree. As well, there was statement that possibly a pharmacist could administer a medication during the process of teaching a patient. Question for ICC: Can we follow the EPIC recommended process for documenting meds given by MD (this would assume not training all MDs to give the occasional medication) | Decision Made at ICC | ICC Discussion: MD in the Inpatient areas will NOT have access to MAR. | 150
2 | Medications will be considered overdue after one hour. Immunosuppressive agents and anticoagulants will be considered overdue after 30 minutes. In discussion, agreed all meds overdue after 60 mins. | Approved by group |  | 152
3 | Discontinued medications will remain in the Active Medications section for one hour after being discontinued. Then, they will move to the bottom of the MAR. | Approved by group |  | 153
4 | Discontinued meds stay on MAR for 24hrs: | Approved by group |  | 154
5 | Nurses can document medication administration from the Work List | Approved by group |  | 155
6 | Users will always scan the patient wristband first to verify patient identity, and then they will scan the medication barcodes. | Approved by group |  | 156
7 | Users will choose the Given by Other action to document administrations given by the patient or family member (e.g. bedside meds). Users will note the name of the other person in the Comments box. Users will choose the Document for Another User button to document a medication given by another clinician. Users will note the name of the other clinician in the Documented for Another field. Discussion: Would this be appropriate for a RACE call? No, there are emergency narrators for several types of situations like a RACE call or code blue. Could there be a co-sign order here if needed to be completed by another RN. No, there is no functionality Do we Document for physicians? Currently yes? But should we? Do we Document for other RN's? Currently no? Currently, if an MD gives a medication, they document that administration in their notes. The nurse would write on the MAR that the med was "given by MD, see notes" or something to that effect. In EPIC, this would be accomplished using the "other provider" feature in the MAR There we comments in the room that is might be "against nursing college standards" to document for another despite the fact that if the RN does not put some note in the MAR then we wouldn't know if the patient got the med without having to read all the MD notes. | Decision Made at ICC | ICC Decision: IP MDs will not be given access to the MAR. CSA: When an MD gives a med to an IP it is witnessed by an RN. The MD then documents in their progress notes and the RN enters 'Given by MD' on the paper MAR. This process will continue with EPIC. | 158
8 | Users will document Hold for any doses that were indicated to be held by provider. Users will supply a reason and enter additional information in the Comments field if necessary. There will be a medication hold order for holding single doses of a medication. If multiple doses need to be held, providers will discontinue and reorder the medication. | Approved by group |  | 159
9 | When preparing medications in the med room, nurses will scan the medications and pend the administration | Approved by group |  | 160
10 | The system will document Rate/Dose Verify when the same rate is entered in a flowsheet and Rate/Dose Change when a different rate is entered in a flowsheet for titratable medications. On the MAR, users will see only Rate/Dose Changes. | Approved by group |  | 162
11 | Loading dose, bolus, and push volumes will be included in the intake totals per medication. Decision accepted Nurses will use an action of Bolus from Bag against a unique med-specific bolus from bag order if the bolus of the medication comes from an already-infusing bag. Physicians don't always know if it is a bag or a bolus. They order the bolus only. That's fine, they can continue to order just bolus and the nurse/pharmacy will supply appropriate meds . What about smart pump implementation? This is recommended to start no sooner than 6 months after implementation. This gives the clinicians time to get used to the basic system. The decision for this has not been made yet. | Approved by group |  | 163
12 | Nurses will use an action of Bolus from Bag against a unique med-specific bolus from bag order if the bolus of the medication comes from an already-infusing bag. | Approved by group |  | 164
13 | Will flushes be ordered for all patients, and the administration of flushes will be documented on the MAR?Follow up: Currently at TOH, saline flushes are not documented on the MAR but there is no objection to doing this. Currently flushes are ordered with a medical directive. | Approved by group |  | 165
14 | Who will order flushes? Nurses per protocol/medical directive MDs Will need to build different protocols for different lines | Approved by group |  | 167
15 | The system will automatically schedule Stopped actions for every New Bag action, based on the medication’s duration. | Approved by group |  | 168
16 | Users will document Stop times for infusion meds on the MAR | Approved by group |  | 518

## Orders & Inf Ctrl
Workstream: Orders and Infection Control |  | Approved Decision | ICC Decision / Discussion | id (Hide column
Direction Setting Meeting: Med Rec
1 | List of statuses for med rec: Unable to assess, In progress, BPMH complete, Reconciliation Complete Add BPMH inappropriate and comment | Approved by group |  | 43
2 | Pharmacy staff and nurses to delete meds from BPMH no longer being taken by patient for provider review | Approved by group |  | 44
3 | Nurse or Pharmacy staff to enter patient's preferred pharmacy | Approved by group |  | 45
4 | Transfer orders - The nurse will release signed and held orders upon patient arrival to unit | Approved by group |  | 46
5 | Transfer med rec - Team with higher level of care will be responsible for transfer med rec | Approved by TOH/UOHI |  | 47
6 | Areas do not require transfer med rec: Endoscopy to floor, cath lab to floor, IR to floor, L&D to Postpartum | Approved by group |  | 48
7 | Start med rec prior to discharge. Yes, and will have option to Pend and Sign | Approved by group |  | 49
8 | Discharge prescriptions print closest to the workstation where they are signed | Approved by group |  | 50
9 | Required Med Rec prevents nurse from printing After Visit Summary | Approved by group |  | 51
Direction Setting Meeting: Advanced Care Planning
10 | If no code status for patient, 'Presumed Full Code' in Patient Header | Approved by group |  | 53
Direction Setting Meeting: Lab
11 | Providers select frequency of Add-on for add-on tests, will still use the phone call to ensure specimen and test is available | Approved by group |  | 58
12 | Frequency of Add-on will print a request out to lab | Follow up during Lab interface/device integration discussion |  | 59
13 | Peak and Trough labs - once timed frequency in order to display on nurses' worklist | Approved by group |  | 60
14 | Morning blood draw time is 0700 | Approved by group |  | 61
15 | Specimen Collection Logic - see trac ticket for details | Approved by group |  | 62
16 | Order Release Times for repeating bloodwork: 0000h and 1000h | Approved by group |  | 523
Direction Setting Meeting: Verbal & Cosign Orders
19 | Entry of wrong Provider when entering verbal/TO - In Basket message to reroute to correct provider | Approved by group | Unit/Clinic managers will monitor this report on a regular basis. Post go-live, if large volumes of declined co-signs, they will investigate and review process | 65
21 | order communication modes: Verbal with readback, telephone with readback, per protocol: no cosign, per protocol: cosign required, ordered during downtime, transcribed from paper, add per medical directive with number | Approved by group |  | 278
22 | MDs can sign other MDs verbal orders and cosigns | Approved by group |  | 279
Direction Setting Meeting: Provider Documentation
Direction Setting Meeting: Neurodiagnostics
25 | Technicians perform neurodiagnostic tests in addition to cardiology tests | Approved by group |  | 72
26 | Both outpatients and inpatients will be scheduled for tests | Approved by group |  | 74
27 | Central scheduling will schedule OP tests; Clerks and technicians schedule inpatient tests | Approved by group |  | 75
28 | Users will not schedule specific technologist, but can be assigned a specific physicians | Approved by group |  | 80
29 | Health records scans EMG results into HER; HGH uses interface | Approved by group |  | 82
30 | 1:1 charge between test order and charge | Approved by group |  | 94
31 | Document interpretations for tests: 1 document for test over multiple days, multiple documents for same test | Approved by group |  | 99
Direction Setting Meeting: Consults
32 | Referring provider will not be required to enter a specific person in consult order | Approved by group |  | 104
33 | Notify consulting service by provider to provider phone call and system list | Approved by group |  | 105
34 | Providers and nurses will consult Allied Health Services via an order, patients will be on a system list for each service | Approved by group |  | 107
Direction Setting Meeting: Respiratory Therapy
35 | Systems list for IP RT patients - broken down by unit/zone or 1 for RVH | Approved by group |  | 109
36 | No charge for Oxygen | Approved by group |  | 110
37 | We don't drop charges for other RT services | Approved by group |  | 111
38 | RT, RNs, MDs collect ABGs (RT or RN will print label for MD) - SFMH ONLY: phlebotomy and MD (PB will print label for MD) | Approved by group |  | 112
39 | SFMH ONLY - notify phlebotomist of ABG collection | Approved by group |  | 113
40 | Retrospective productivity reporting - Task completion with default work units with retroactive adjustment PRN, choose additional tasks to track other productivity, add tasks for teaching RT students | Approved by group |  | 115
41 | Nursing and RTs collect sputum samples | Approved by group |  | 521
41 | Nursing and RTs collect sputum samples | Approved by group

## Stork
Workstream: |  | Approved Decision | ICC Decision / Discussion | id (Hide column
Direction Setting Meeting: L&D Patient Management
1 | The unit clerk, registration, and all labor and delivery nurses will have security to arrive and bed expectant mothers as they present. | Approved by group |  | 176
2 | Registration staff will scan in the paper records for patients who do not receive prenatal care into Epic at 20 weeks. Need to revisit who will be doing the scanning and if it will be the RN or Registration L&D staff. | Approved by group |  | 188
3 | Unit clerks or nurses will upgrade patients from Assessment to Admitted in addition to assuming them a room and bed. This action changes the patient class from Outpatient to Inptatient | Approved by group |  | 177
4 | L&D registration or central registration will complete patient registration. Preference is to have L&D clerk or nurses be able to update information on the patient. | Approved by group |  | 178
5 | Nurses can sign triage order sets per protocol | Approved by group |  | 179
6 | Nurses will create a chart for the newborn when delivery is imminent | Approved by group |  | 181
7 | The nurse will admit the baby from the Delivery Summary. Unit clerks will admit the baby from the L&D Manager/L&D Grease Board | Approved by group |  | 182
8 | The nurse will be responsible for marking the patient as delivered | Approved by group |  | 183
9 | Providers will addend Delivery Summary information if they need to add more information | Approved by group |  | 184
10 | Nurses and unit clerks will create new patients records for patients that are not pre-registered and arrive in the L&D | Approved by group |  | 189
11 | Clerks and Nurses will enter results information for patients who did not receive prenatal care in the Results Console. | Approved by group |  | 190
Direction Setting Meeting: Operative Deliveries
1 | Unscheduled C-section: Nurses or unit clerks will create surgical cases on-the-fly for emergent C-sections. Decision agreed TOH - Yes HGH – follow up required – right now it’s a phone call | Approved by group |  | 147
2 | L&D Nurses and L&D unit clerks will be able to create surgical cases (TOH): Decision accepted:c/s main OR – Main OR schedule the case – shadow current process OR Nurses and OR unit clerks will be able to create surgical cases (HGH) Add:the nurse in the inpatient clinic will be able to create surgical cases (HGH) Decision:OR scheduling staff and Inpatient clinic nurse | Approved by group |  | 141
3 | Scheduled C-section: Obstetricians can enter orders for a patient prior to the day of surgery. These orders will be signed and held and released by the nurse on the day of the surgery. | Approved by group |  | 142
4 | Nurses will drag and drop patients to the L&D OR/PACU or the Main OR/PACU on the L&D Manager to reflect the patient’s actual physical location. Decision: TOH- Nurse and or unit clerk HGH – drag and drop moving of patient will function differently – will need to be able totransfer them to the different units – L&D nurse goes to c/s in main OR so they will need access to the same documentation and access to delivery screens regardless if you deliver in the main OR or LD | Approved by group |  | 143
5 | Scheduled C-section: Along with the Brief Operative note, Obstetricians will write a Delivery note but will not be required to write a Full Operative note (as the Delivery note contains the operative documentation from the procedure). Alternative: along with the Brief Operative note, Obstetricians will write a Delivery note and a Full Operative note. | Approved by group |  | 145
6 | Unscheduled C-section: What is the workflow to contact anesthesia for an epidural? TOH - Page them No formal schedule that anaesthesia works from – but they do come look at whiteboard - TOH HGH – call them | Approved by group |  | 146
7 | nscheduled C-section: Charge nurses, unit clerks, and L&D registration staff will be responsible for back-scheduling the on-the-fly cases before the patient is discharged. Decision - TOH agrees HGH - if happens in the middle of the night then will need a workflow that allows it to be done the next day | Approved by group |  | 149

## Willow
Workstream: Willow Inpatient |  | Approved Decision | ICC Decision / Discussion
Direction Setting Meeting: Dispensing
1 | All sites will use Dispense Checking. Pharmacists and/or Technicians will be performing the check. | Approved by group
2 | All sites are interested in using Dispense Tracking. Pharmacy staff (technicians, porters, pharmacists) will be the primary users for sending and receiving. | Approved by group
Direction Setting Meeting: Investigational Medications
3 | Proxy medications will be used for medication alert checking of investigational medication records when appropriate (as specified by study protocol). | Approved by group
4 | A placeholder investigational medication record will be ordered when ordering providers or study coordinators cannot find an investigational medication or if an admitted patient is part of a study at another hospital. | Approved by group
5 | Medications used in research studies will be prefixed with INV, <Research Study #>, and <Medication Name>. If the medication name should not appear to users (e.g. if a study is single or double-blinded), a study drug name will display in its place. To indicate to providers that a product is being ordered, not just a study, research medications will be designated as an Investigational product. | Approved by group
6 | Reference links to study protocols (when appropriate) will be available to providers in order entry, verification and on the MAR. | Approved by group
7 | Pertinent study information will be available to pharmacists when clinical staff associate the order to the study. (i.e. once a physician indicated the order as "research associated" the pharmacist will be able to see the study info (but not the patient ID) in verification. | Approved by group
8 | There will be an investigational-specific label, on which will appear the phrase "For Investigational Use Only". | Approved by group
9 | Each investigational medication will have its own record. If the medication is used in multiple studies, there will be a different record for each study. | Approved by group
10 | All sites will continue their current medication labeling and printing process for investigational medications. | Approved by group
11 | Investigational medications associated with expired studies will be identified by the study coordinator, and they will be hidden from database selection and removed from preference lists by the Willow project team. | Approved by group
12 | All sites will continue to use their Clinical Trials Management System (CTMS) to document investigational-specific notes and details.
Direction Setting Meeting: Pharmacy Interfaces
13 | Once live, the pharmacy project team (centralized Willow team) will initially be responsible for managing ADS errors. | Approved by group
14 | All sites currently send, and will continue to send all orders to the ADS/ADC. | Approved by group
15 | Patient-specific bins will not be used in ADS/ADCs due to space constraints. | Approved by group
16 | All sites: Nurses can mix medications from components stored in ADS. At TOH, and RVH: nurses can pull multiple strengths for a medication to make up a total dose, which can also be accomplished in EPIC (Note: HGH currently currently enters 2 strengths separately due to an interface issue with Anzer). | Approved by group
17 | Allergies will not be displayed on the ADC/ADS. | Approved by group
18 | All sites currently send both CSN (encounter #) and MRNs to the ADC/ADS and display the MRN. | Approved by group
19 | Only RVH (and soon SFMH) currently use remote stock and virtual drawers, this will continue to be possible with EPIC. | Approved by group
Direction Setting Meeting: Medication Ordering
20 | Patient Contexts Configuration: Contexts are set up with the following age ranges (once verified as consistent with CHEO) o Neonate: 0 - 4 weeks o Infant: 4 weeks - 1 year o Pediatric: 1 year - 14 years o Adult: 14 years - 150 years | Approved by group
21 | Medications not ordered in weight-based units for patients that are under 14 years of age will back-calculate and display the dose in weight-based units | Approved by group
22 | Dual pharmacist verification will not be required for any orders at this time. | Approved by group
23 | System level liquid rounding will be used to apply more granular dose rounding to smaller volumes (when not specified within the medication record). | Approved by group
24 | The project team will pre-build common "And" linked order panels for medications or medication/procedure combinations that are commonly ordered together. | Approved by group
25 | The project team will pre-build common "Followed-By" linked order panels for medications with a defined number of tapered doses. For tapers with a variable number of doses, build a linked order panel on-the-fly in order entry. | Approved by group
26 | The project team will pre-build common "Or" linked order panels for medications that can be administered via multiple routes. When necessary, build "Or" order panels on-the-fly in order entry. | Approved by group
27 | For PCA medication orders, providers will enter the PCA parameters in the Questions section of the Order Composer. | Approved by group
28 | Titration parameters will be entered in the dose field and explained in the administration instructions. | Approved by group
29 | Administration instructions, order duration and infusion rate changes do not require pharmacist verification, as long as it is within allowable range. | Approved by group
30 | Reasons will not be required to discontinue medications. | Approved by group
31 | For patient-supplied medications, physicians will select the patient-supplied checkbox and may enter the number of doses provided by the patient if known. | Approved by group
32 | Labels will be printed for patient supplied medications so it can be supplied for barcoded medication administration. | Approved by group
33 | When a physician needs to order something not available on the facility preference list, she/he will use the non-formulary medication record. | Approved by group
34 | Weight will be required to sign weight-based medication orders. | Approved by group
35 | Medication orders that are due now will be scheduled to the nearest 15 minutes. | Approved by group
36 | Pharmacists will resolve a non-formulary medication order by changing the product at verification. | Approved by group
Direction Setting Meeting: Medication Labels
37 | The following fields will be bolded on all medication labels: Patient Name, Med name, Dose. | Approved by group
38 | Rate will appear on labels with the exception of continuous or titratable infusions. | Approved by group
39 | Administration instructions will not print on labels. | Approved by group
40 | Label Comments will print on 'non-production' medication labels. | Approved by group
41 | Production labels will be printed for all pharmacy prepared mixtures. | Approved by group
42 | Preparation Instructions will only print on 'production' labels. | Approved by group
43 | Patient labels will print for all patients served by a cart, regardless of whether patient has orders. | Approved by group
44 | ADS Load label will print as notification to stock a medication in ADS. | Approved by group
45 | Due times will not be printed on labels. | Approved by group
46 | Take home labels will be used for meds sent home with patients. | Approved by group
47 | A label will be printed for patient supplied medication. | Approved by group
48 | Final signoff for label design will the responsibility of pharmacy and nursing. | Approved by group
Direction Setting Meeting: Pharmacy Autoverification
49 | All sites agreed to autoverification of medication orders in some areas, under certain circumstances: ED – non admitted patients - YES to autoverify ADC/Floorstok meds: All sites - NO to autoverify Meds dispensed patient specific from pharmacy: All sites ED – boarder patients - NO to autoverify (all orders need prospective review): All sites PACU - YES to autoverify ADC/floorstock meds for PACU Phase of Care only: All sites - NO to autoverify post op orders: All sites | Approved by group
50 | Retrospective review after autoverification is a read-only review and will not be required. | Approved by group
51 | All Sites will continue to have a mix of profiled/non profiled ADCs. | Approved by group
52 | Override pulls from ADS will not need retrospective verification by a pharmacist, but will be reportable. | Approved by group
53 | Prospective order verification will be required for boarder patients in ED. | Approved by group
Direction Setting Meeting: Medication Charging & Crediting
54 | ADC interface will be used to document waste. | Approved by group

## OpTime
Workstream: |  | Approved Decision | ICC Decision / Discussion | id (Hide column
Direction Setting Meeting: OR and Procedural Charging
1 | Charging for OR Time based on Level-setting criteria: | Dynamically-assigned levels, based on other rule-based criteria
2 | Supply and implant charging | Contaminated - cost Dropped - cost Opened not used - cost, billed Other - based on chart review Damaged - cost not billed, sometimes returned to vendor Procedure change(e.g. supplies opened and procedure changed) - charged not billed Surgeon changed mind - cost not billed Wrong size - cost not billed Damages as implanted - charged not billed Expired - costed not billed, falls under same window as damaged Misplaced (implanted or explanted) - typically not captured
3 | Will any supply or implant be marked up for non-OHIP patients? | No
4 | Will any supply or implant be marked up for OHIP patients? | No
5 | Capturing time charges in pre-op(SDCU), PACU, and Phase II | Looking at PACU based on OR level and time level, will use 15 minute intervals Not stratified but time intervals to be tracked. Time intervals to be 15 minutes
6 | Supply charging in non-intra-op areas | NO and we do not wish to charge for this in future
Direction Setting Meeting: OR Full Peri-OP Nursing
1 | do you have an algorithm in PAU to determine the type of visit? | Yes, All sites
2 | Who is responsible for coordinating scheduling of the PAU appointments? How are these requests triaged, and by whom? | TOH - registration and booking HI - PAU clerk, admitting does not have responsibility. HGH - OR clerk
3 | Who is responsible for writing the H&P in PAU if one is not already written? | Surgeons
4 | Do you schedule labwork done as part of a PAT visit, or do you coordinate visits with any other departments for PAU? | Yes (ALL Sites) have labwork scheduled. At Civic PAU nurses complete labwork, other sites send patients to the lab.
5 | What kind of procedures are performed in pre-op (SDCU)? | DI angio fusions (civic) Renal biopsies L&D Regional anesthesia – nerve blocks pre-op (not prepped in surgical daycare) Dressing changes HI - Biopsies (heart), right heart caths, angio, EP procedures, HGH - pre-warming, clipping
6 | When an endoscopy or L+D procedure is performed in the OR, is it treated as a surgery (subject to at least the documentation requirements of a procedure done in the OR), or is it considered an extension of the Endo or L+D rooms? | Renfrew - all ENDO in OR ENDO in OR (TOH) - MDs do reporting HGH- documentation done through GMED
7 | What procedures do you perform in PACU? | cardioversion, dressing changes, nerve blocks (pre, post, interventional), ECT therapy, GA for MRI prior to transfer to MRI suite - emerg in PACU.
Direction Setting Meeting: Endoscopy Nursing
1 | Endoscopy clerical staff currently schedule procedures | Yes
2 | Gastroenterologists or general practitioners will submit procedure requests using case request orders, which are routed to the endoscopy clerical staff. | Yes
3 | Endo patients are recovered on the endoscopy unit by endo nursing staff | Yes
4 | On occasion, you will route patients through SDCU or PACU units. Under what conditions would a patient be routed from or two a unit other than endo? | Yes, If GA
5 | Will you perform any kind of follow-up or post-procedure call workflow? | No
6 | Do you require any kind of pre-procedure orders placed by the physician ahead of the procedure for care in pre-op? | In Physicians Office
7 | Where are bronchoscopy procedures recovered? | Endoscopy Unit
8 | Do documentation requirements change depending on the type of procedure (e.g., for bronchoscopies, versus endoscopies?) | No
9 | Under what conditions will Anesthesia perform sedation instead of an endo nurse? | Difficult pt, pt tolerance, pt with ICD, HGH anesthesia is present with all cases.
10 | Do your documentation requirements change for off-unit procedures? | Yes
11 | How do you schedule capsule/motility procedures? | Direct consults to the physicians
12 | What documentation is required for these kinds of procedures? | Nursing documentation not applicable
13 | Who will be responsible for discharging patients (GI nursing, support staff, or using an automatic batch at the end of the day)? | A nurse on the unit
14 | Will physicians continue to document CIRT in EndoPro?? | Yes
15 | Will GI doctors use electronic case request? | Yes
Direction Setting Meeting: Surgeon Workflow
1 | Surgeons will electronically request cases using case request orders | Yes
2 | When will place pre-op orders electronically in Epic ahead of the day of surgery, or simultaneously with the case request order. | At decision to treat
3 | Do Surgeons currently code their case requests with a CCI code. | No
4 | A patient H&P may be written by a midlevel or resident, although residents must clear the history with the MRP. | Yes
5 | A patient H&P may be written by a midlevel or resident, although residents must clear the history with the MRP. | Yes
6 | Surgeons will be required to enter a brief op note or an operative note immediately after surgery | i:If the operative note is not completed immediately after surgery, it must be completed within 24 hours of the surgery. ii:Residents or advanced care practitioners may write the full op-note, but the surgeon must cosign the note.
7 | Surgeons are required to reconcile all medications, including outpatient prescriptions (or prior-to-admission medications) and hospital-delivered care and medications. | Yes
8 | Surgeons are not required to reconcile anesthesia orders or medications. | Correct

## Anesthesia
Workstream: |  | Approved Decision | ICC Decision / Discussion | id (Hide column
Direction Setting Meeting:

## Radiant
Workstream: |  | Approved Decision | ICC Decision / Discussion | id (Hide column
Direction Setting Meeting:
Nuclear Medicine | Atlas Alliance schedulers will use a panel appointment structure to schedule Nuclear Medicine series procedures. Drag and Drop scheduling will be used for single procedures. | By Group |  | 455
| Nuclear Medicine Technologists will document radiopharmaceuticals as medications in Hyperspace. | By Group
| Nuclear Medicine Technologists will have access to add and remove appointments as necessary from the panel. | By Group
| Nuclear Medicine Technologists will NOT mark patients as radioactive. | By Group
| Radio pharm will be ordered in EPIC at the time of protocol by Nuclear Medicine Charge Tech or NM MD or when the patient arrives by the tech. | By Group
| Charge Capture - Multiple exams will NOT be charged on the first day of the appointment for Nuclear Medicine | By Group
Charging | DMI Technical charges do not include the cost of contrast. | By Group |  | 503
| We do not charge for sedation | By Group
Mammo | Technologist will use the breast image documentation within Epic. | By Group |  | 474
| Technologists will order and administer exam-related medications (e.g. lidocaine for biopsies). | By Group
| Breast cancer risk assessment will not be performed in Epic. | By Group
| Epic will store breast cancer risk assessment info (especially for high risk patients). | By Group
| Assessments will be documented at both the overall and individual breast level. | By Group
| All breast exams except biopsies will document assessments. | By Group
| One-click normal macros will be used. | By Group
| Pathology will be documented in Epic. TOH has an off-site consultant/employee entering this information. At other sites, there is clerical staff that could do this data entry. | By Group
Non-Invasive | Technologists will have the security to change procedures as appropriate with an order mode of per protocol or verbal (if had to consult the ordering physician, radiologist, or cardiologist). | By Group |  | 592
| Technologists will be able to change exams between modalities per each site's protocol. | By Group
| The authorizing physician will not be required to co-sign the changed order. | By Group
| Technologists will be able to cancel orders as appropriate per policy. | By Group
| Technologists will be able to finalize protocols per the medical directives. | By Group
| Technologists will be able to route protocols to a radiologist or pool of radiologists if necessary. | By Group
| Technologists will not place orders for lab tests in Epic as part of the protocoling process. | By Group
| Technologists will document supplies in Epic. | By Group
| Technologists will document radiation (including fluoro time) in Epic. | By Group
| Charge technologists/radiologists will order contrast as part of protocoling. Technologists will also have the ability to order contrasts during their begin/end exam documentation if necessary. | By Group
| The imaging physician will be the authorizing physician for contrast. | By Group
| Pharmacy will not need to verify contrast orders. | By Group
| Pending equipment availability, technologists will barcode administer contrast on the MAR. | By Group
| Sonographer reports will stay in PACS and PowerScribe (follows current workflow). | By Group
| Technologists will use tech rover for portable exams where devices are available. | By Group
ED | As soon as an order is signed, it will appear for the technologist. Critical or life-threatening orders that need to be completed immediately will also be called in to radiology in addition to CPOE. | By Group |  | 438
| ED and imaging will use the Pt Rad Status button, but only to communicate that the patient is not ready for radiology. | By Group
RAD Workflow | Tentative decision: The radiologist reading workflow will be PACS-driven and the reading work lists will reside in PACS. | By Group |  | 459
| Radiologists will protocol exams in Epic prior to scheduling. | By Group
| Radiologists will have the ability to change an order as part of protocoling. | By Group
| Radiologists will order day of exam related medication (Lasix) as part of protocoling but contrast pre-medication will be the ordering/referring doc's responsibility (but will be indicated in the protocol). | By Group
| Radiologists will place contrast orders as part of protocoling. | By Group
| Radiologists will indicate during protocoling when a patient needs labs prior to the procedure. | By Group
| Critical results will be tracked in Epic if the PowerScribe solution is not available. | By Group
| Tracking interesting studies will remain in PACS. | By Group
| Teaching studies will remain in PACS. | By Group
| For technologist quality, TOH will continue to PeerVue while other sites will track technologist quality in Epic. | By Group
| Radiologists will sign results in PowerScribe. | By Group
| Radiologists will create and sign addenda in PowerScribe. | By Group
| TOH will continue to use PeerVue for radiologist peer review while other sites will peer review in Epic. | By Group

## Cupid
Workstream: Cupid |  | Approved Decision | ICC Decision / Discussion | id (Hide column
Direction Setting Meeting: ECG and Echo Stress
1 | Physicians will place an order for generic stress procedure and answer a question to indicate the type of test to be performed | Approved by group |  | Trac 501
2 | Delegated order- technologists will be able to enter stress agent orders, administration, and IV placement | Approved by group |  | Trac 501
3 | Technologists will document cardiac stress preliminary result findings for physicians in Epic, including stress summary - Renfrew technologists will document stage data within EPIC - Other sites will depend on interface scope - ideally, discrete data can interface into EPIC, otherwise PDF results will be interfaced | Approved by group |  | Trac 501
4 | Echo stress procedures will continue to be resulted in Xcelera | Approved by group |  | Trac 501
Direction Setting Meeting: Cath and EP Lab Pre/Post Workflow
5 | Cardiologists/Fellows will place pre-procedure orders for patients in Epic | Approved by group |  | Trac 492
6 | Pre-procedure staff will track completion of pre-procedure tasks and pre-procedure phone call using Procedure Pass functionality in Epic | Approved by group |  | Trac 492
7 | Clerks and care facilitators/charge nurses will assign patients to specific prep/recovery bays via the status board | Approved by group |  | Trac 492
8 | Cath cardiologists will reconcile cardiac meds only. If the patient is going back to the ward, the receiving physician will perform order reconciliation post-procedure. | Approved by group |  | Trac 492
9 | Day Unit nurses will discharge outpatients after their procedures | Approved by group |  | Trac 492
Direction Setting Meeting: Vascular Ultrasound
10 | Sonographers will begin and end exam in EPIC for turnaround time tracking | Approved by group |  | Trac 527
11 | Current state reading workflow will continue when EPIC goes live and results will be interfaced into EPIC chart - TOH yes; HGH will need to f/u for resulting workflow | Approved by group |  | Trac 527
Direction Setting Meeting: STEMI
12 | Emerg department staff will begin STEMI documentation in the ED using the STEMI Narrator | Approved by group
13 | Will the Cardiology resident/fellow document a note outline of inital STEMI Evaluatio? WHen will they complete this note? | Approved by group for resident/fellow documentation of inital STEMI Evaluation during pre procedure
14 | How will Emerg department contact Cardiologist Cath Lab staff of a possible STEMI: Options Consult +announcement +Page, Phone call and Other | Approved by group for annoucement and page |  | Trac504
15 | For After-hours STEMI (Bypassing ER), Staff be able to perform a quick admit of patients. Admitting will update any generic admission registration fields after patietn is stable | Approved by group |  | Trac 496
16 | Who will be responsible for creating the STEMI case for Emerg Bypass patients during regular business hours? After Hours? | Approved by group for regular hours: Care facilitator, After hours: CCU charge nurse or Coordinator |  | Trac498
17 | Who will have access to the STEMI Button | Approved by group for CCU Nurse, RN Coordinator, Cath Lab nurses |  | Trac499
18 | What event will constitute "Ballon time" | From the time the patient enters a medical facility to the time that the first device gets to the lesion. |  | Trac502
Direction Setting Meeting: Holter and Event Monitoring
19 | · Technologists will collect the ID number for monitors during hook-up appointments o Can select ID number from dropdown, but the ID will not be hidden if the monitor is in use. | Approved by group |  | Trac506
20 | · Staff will track monitor returns using the status report in Epic | Approved by group |  | Trac507
21 | · Schedulers will not create an additional appointment for the monitor return. | Approved by group |  | Trac508
Direction (TTE) Workflow
22 | · Clerks will schedule/add-on inpatient echo procedures [for all sites] | Approved by group
23 | · When contrast is needed the tech will order it "per medical directive" and document the administration of it. | Approved by group |  | trac501
24 | · Technologists will begin and end exam in Epic for turn around time tracking | Approved by group |  | Trac501
25 | · Technologists will be able to choose "performable" procedure in the end exam navigator | Approved by group |  | trac501
26 | · Cardiologists will continue to result echo procedures in Xcelera | Approved by group |  | trac501

## Beacon
Workstream: Beacon |  | Approved Decision | ICC Decision / Discussion | ID
Direction Setting Meeting: Application Kickoff
1 | Physicians will be granted access to add problems to the problem list | Approved by group |  | 357
2 | Physician will have access to change the diagnosis | Approved by Group
Direction Setting Meeting: Oncology Consult
3 | TOH will use the AJCC for for Cancer Staging | Approved by Group |  | 358
4 | Only physicians and pathologists will be given the security to sign the staging forms | Approved by Group
5 | Coders will receive an automatic notification through in-basket of signed stages and can add the diagnosis and staging for CCO | Approved by Group
6 | The first order in a treatment plan always has to be a staff physician. Any subsequent orders can be made by fellows and/or residents. | Approved by Group
7 | One single weight will be used for dosing throughout the treatment plan | Approved by Group
8 | The line of treatment associated with every chemotherapy regimen will be made optional | Approved by Group
9 | The treatment plan goal associated with every chemotherapy regimen will be mandatory. There will be a "hover to discover" description for each goal to ensure consistency amongst physicians | Approved by Group
10 | When physicians create a new treatment plan for patients they are required to indicate a start date. In the meantime, all of the data is sent out for approval and sometimes that start date may require adjusting due to approval. It was decided that the booking clerks would be given security to edit the start date so patients are not being given treatment before they have been deemed approved for funding. | Approved by Group
11 | A provider will be notified if there is a 10% change in the patient's weight of BSA | Approved by Group
12 | Weight-based medications will be recalculated each time the dose is due for administration, however the dose will not automatically change | Approved by Group
Direction Setting Meeting: Managing Oncology Treatment
13 | Providers will make percentage based dose modifications based on the current dose but with the awareness of the original dose | Approved by Group |  | 359
14 | Users should be required to document a reason for the change of orders as long as there is an option for "other" | Approved by Group
15 | Orders in the treatment plan will become unsigned if treatment is deferred more than 7 days and will require physicians to reevaluate the treatment | Approved by Group
16 | An appointment request to see a physician will be made if a treatment is deferred more than 14 days | Approved by Group
17 | Only physicians are responsible for discontinuing a treatment plan | Approved by Group
18 | Only physicians can take a treatment plan off "hold" | Approved by Group
19 | Only staff physicians can add future treatment plans and initiate the treatment plan | Approved by Group
20 | Pharmacists will reconcile the patient's treatment plan when a patient has received treatment at an outside facility | Approved by Group
21 | Pharmacists will reconcile the patient's cumulative dose history when a patient has received treatment at an outside facility | Approved by Group
Direction Setting Meeting: Post Treatment Follow-up
22 | Current practice for providing treatment summaries will remain. Only patients in survivorship program will get a treatment summary (Breast, endometrial, and colorectal only) | Approved by Group |  | 361
23 | All staff will have access to view oncology history | Approved by Group
24 | Oncology users will be given security to edit oncology history | Approved by Group
Direction Setting Meeting: Oncology Patient Engagememt
25 | The After Visit Summary will be given to the patient and will include the MyChart sign up information for patient portal | Approved by Group |  | 362
26 | Patient can access and complete questionnaires in MyChart and will be linked to his/her visit | Approved by Group
27 | Disease groups will be included in MyChart so patients can view information unique to their condition | Approved by Group
Direction Setting Meeting: Oncology Lab
28 | Labs will be built within the protocols for the treatment plan and will be scheduable within the treatment plan | Approved by Group |  | 363
Direction Setting Meeting: Oncology Population Management
29 | TOH will use the Cancer registry to create reports to be sent to CCO | Approved by Group |  | 364
30 | Foundation System registry metrics will be used to track the types of encounters for oncology patients | Approved by Group
| The following patient groups will be tracked: - by providers and providers will track their own individual patient populations - by specific treatment protocol - based on treatment goal plan - based on treatment plan start date - based on how long they have been treated - discontinued treatment plans - Survivorship patients -Research patients are tracked by specific clinical trail -Research patients are tracked by specific study branch (i.e. specific protocol within the research study) - Patients on medications with a lifetime dosing maximum - Patients are tracked by oncology-related surgeries they've had - Patients receiving oral chemotherapy - Patients receiving palliative care - Patients with a family history of oncology | Approved by Group
Direction Setting Meeting: Cogito - Beacon Reporting Orientation
Direction Setting Meeting: Oncology Access
45 | Clinic and infusion appointment requests will be included in treatment plans | Approved by Group |  | 365
46 | The checkout activity will be used to schedule next appointment | Approved by Group
47 | The infusion duration table will be used to calculate default infusion times | Approved by Group
48 | Follow up will be completed in the wrap up activity | Approved by Group
Direction Setting Meeting: Inpatient chemotherapy Treatment

## Outpt Core
Workstream: |  | Approved Decision | ICC Decision / Discussion | id (Hide column
Direction Setting Meeting: Office Visit - #341
| Support staff will room patients and enter a chief complaint, vitals, history, and other information prior to the provider seeing the patient | Approved by group |  | 284
| Patient goals will be tracked. | Approved by group |  | 284
| Support staff will be able to enter orders for patients per protocol based on the medical directives of the hospital | Approved by group |  | 284
| SmartTools will be used to document encounters. | Approved by group |  | 284
| Note and diagnosis are both required to close an encounter. | Approved by group |  | 284
| To resolve erroneous documentation - The SmartSet? called "erroneous documentation" will be used to indicate the documenting in wrong chart. - The user will first rewrite the information into the correct chart. - The user will then remove/delete the information that was documented in the wrong chart. | Approved by group |  | 284
| Barcode scanning is not used currently across the Altas partners when documenting the administration of immunizations and is not in scope. | Approved by group |  | 284
| Patient problem list updates: Anybody should be able to update problem lists, it is patient centered not physician’s centered. | Escalated to ICC | Approved by group | 284
Direction Setting Meeting: Clinic Support Visit - #2731
| Clinical support visits will be scheduled with a generic support staff book rather than individual support staff. | Approved by group |  | 338
| Support staff will enter orders per protocol following the medical directives of the hospital. In some cases, the user might have to specify the medical directive that they are following. It will not appear in the dropdown, they would have to put it in a note. | Approved by group |  | 338
| For medical directives: no co-signs are required, may be some unique circumstances. Can also perform an audit to ensure that the support staff are choosing the correct status when placing orders. | Approved by group |  | 338
| The Clinical Support encounter will convert to an Office Visit if the encounter provider is changed to a physician. | Approved by group |  | 338
| Support staff will be required to complete the following to close a clinical support encounter: Immunization administration, Medication administration, Signing all pended orders or medications, Diagnosis will be recommended not required. | Approved by group |  | 338
| The following fields will be required when administering an immunization: Date, lot number, DIN, manufacturer, dose, site, route, administering user. For injection site, this can be configured and will be decided upon in the clinical content sessions. | Approved by group |  | 338
| Social workers will be able to use patient lists and care teams to track their interactions with the patient. | Approved by group |  | 338
| Social workers will be able to document their own notes. | Approved by group |  | 338
| Social workers are responsible for closing their own encounters | Approved by group |  | 338
| Alert to nurse about missed appointments--no pop up will appear, it will be identified upon scheduling an appointment. | Approved by group |  | 338
Direction Setting Meeting: Outpatient Procedure Visit - #2649
| No protocol prior to an ambulatory procedure will be incorporated to the workflow. | Approved by group |  | 350
| Charges for common in-office procedures will be automated based on provider documentation in procedure forms and providers will review charges for procedures in the charge capture pop up. | Approved by group |  | 350
| Procedures with a one-to-one match between the order and the charge will have the charge drop automatically regardless of whether or not a specific form exists in Epic’s Foundation System | Approved by group |  | 350
| Procedures with a one-to-many match between the order and possible charges will have the charge drop automatically if a specific form exists in Epic’s Foundation System | Approved by group |  | 350
|  | Approved by group |  | 350
Direction Setting Meeting: Medication Workflow (In clinic and prescription) - #345
| Prescriptions will default to print. Fax will still be an available option. | Approved by group |  | 387
| Any prescription can be faxed, though some medications (like narcotics) require certain format/information to be included for release. Quebec requires certain disclaimers to be placed on all faxes. | Approved by group |  | 387
| When a provider is entering a prescription medications, he will not be required to enter a diagnosis and there will be no need to link it to a diagnosis. | Approved by group |  | 387
| Support staff can order prescriptions based on medical directives. A comment field will be required to specify which medical directive is being used. | Approved by group |  | 387
| Sample medications can be ordered and documented in Epic. | Approved by group |  | 387
| No additional documentation required for Sample medications. | Approved by group |  | 387
| Support staff can enter orders for injections per protocol based on the directives set by the hospital. | Approved by group |  | 387
| Clinic administered medications will not require a diagnosis. | Approved by group |  | 387
| The person who administers a medication will be responsible for documenting the administration.The button allowing for another person to document should not be available/visible. | Approved by group |  | 387
| Any non-immunization medications given in the clinic drop a charge for medication only, not administration. | Approved by group |  | 387

## Bones
Workstream: Bones |  | Approved Decision | ICC Decision / Discussion | id (Hide column
Direction Setting Meeting: Bones Kick-off
1 | We will add the 'Studies to Result' column on the multi provider schedule and use 'Visit Events' to track patients who have left the department to go to x-ray. | Approved by Group
2 | The Nurse will be responsible for entering injection details into the system prior to physician administration. This will help make the physician workflow more efficient. Injection documentation includes drug name, Lot# and expiry date. | Approved by Group

## Grand Central
Workstream: |  | Approved Decision | ICC Decision / Discussion
| Direction Setting Meeting: Admissions, Transfers and Discharges #1840 |  |  | Tue Dec 12 14:00
1) | When will a patient be considered ‘admitted’? | Patients will be admitted in Epic when they are in Admitting - bed planning workflows
2) | Who will complete a patient’s scheduled admission? | An admitting clerk. To be verified with SFMH
3) | Will this be the same for direct admits? | Yes
4) | Will an admit order be required for admission? | Yes
5) | Will bed planners always be involved in the admission process? | Always. This will be a nursing supervisor, coordinator, or manager at the smaller hospitals; this can include patient flow managers and registration clerks.
6) | How is bed planning notified that a bed is needed? | HGH: paper request TOH: phone call that generates an RFA missing other partner information
7) | What information do bed planners need to plan for a direct or scheduled admit? | Service Level of care Accommodation code Gender MRP Diagnosis Insurance coverage Special bed requests Other necessary equipment
8) | Will bed management be the only staff able to make bed assignments? | No; the patient floor manager, registration clerk, and other staff will be allowed to do so.
9) | Will bed planning place the patient in the new bed in every transfer? | To be determined in Direction 2.
10) | Who will complete a patient transfer? | Unit clerk, bed planning, nurses.
11) | Who will be responsible for requesting transport during transfers? | To be determined in Direction 2
12) | Who will complete the patient’s discharge? | Nurse
13) | Who will complete the patient’s discharge for deceased patients? | Nurses currently pronounce a patient as deceased, but a physician is required to complete chart.
14) | If information is missing for deceased patients (date/time/cause of death), who will be responsible for populating this information? | Nurses and/or clerks.
15) | Who will be responsible for requesting transport during discharges? | Nurse and/or unit clerk
RVH does not have patient transport so nurses also complete the transport.
16) | Event Management Grid, completed during session:
| Direction Setting Meeting: Patient Movement Direction Session #3208 |  |  | Mon Dec 11 16:00
Our Patient Movement Direction Session was informational only and did not include specific decision points. Please let Janie and Carolyn know if you would like more information.

## Prelude
Workstream: |  | Approved Decision | ICC Decision / Discussion | id (Hide column
Direction Setting Meeting:
Registration for Lab Direction : Session #2223
* no true decisions were made during this session, lost sight of the registration aspect*
15) | Will the same lab system be used across Atlas? | The goal is to standardize most/all processes. TOH - Cerner and Powerpath Barry's bay - Omnitech currently but they are in the process of selection a new lab system - need to follow up. RGH - Cerner HGH - need to follow up
16) | Do you receive specimens externally and bill for them? | Yes

## Cadence
Workstream: |  | Approved Decision | ICC Decision / Discussion | id (Hide column
Direction Setting Meeting: Appointment Scheduling and Communication #3220
1) | Will there be Centralized vs. Decentralized Scheduling? | The consensus was no centralized scheduling at this point. HGH is talking about perhaps trying to implement this after go live | TRAC 547
2) | Should the system prevent schedulers from scheduling outside their clinic location? | No. They should be able to book everywhere.
3) | Should the system prevent schedulers from scheduling outside their speciality | No. They should be able to schedule everywhere
4) | Do you want the system to restrict scheduling based on patient preferences, such as provider gender when scheduling? | No. The preference can be set, but it may not be met due to wait times it would create. I also want to make clear that when scheduling, the patient preferences check box needs to be checked in order to “restrict” the schedule. This is a default that can be turned off. So in conclusion, the patient preferences check box can be defaulted as not selected and if the schedulers would like to see if the patients preferences can be met, they may then select the checkbox to view such a schedule
5) | Third Party Interpreters? | a) Renfrew has a list// b) Hawkesbury has a third party they call //c) St-Francis uses employee lists of people that speak the language// d) TOH has a third party- MCIS OIS, don't know
6) | Do you schedule interpreters for inpatients? | Yes
7) | Do you track the amount of time interpreters actually spend with patients? | Yes, by the hour. This could be tracked better
8) | Do you cancel interpeters on short notice? | Yes ( 24hr at tOH, encouraged to do at least 48hr - otherwise gets charged) Reports can be available to ensure this is met.
9) | Who maintains provider schedules today? | Individual systems, individual providers at their own partner sites (Hawkesbury) Clerks at TOH maintain Clinic by Clinic
Front-End Revenue Cycle Part 2 - Provider Not in System: Session # 3252
10) | Will provider on the fly be used? | Yes | TRAC 488
11) | Any user able to enter an appointment should have access to this functionality? | Yes. Including some technologists | TRAC 500
12) | What hard stops are needed to create POTF? Name, Address, Fax? | I believe we will be making all fields recommended instead of hard stops, other than the name, which is required to make the POTF record. | TRAC 488
13) | Which Generic providers are needed? | We know we will need them. Unsure of all clinics at this time. Information will be gathered during the Department Managers breakout sessions. | TRAC 529,530,533
14) | Can the POTF authorize orders? | Yes, otherwise they would not be able to do the ordered work. The POTF is not Medications Authorizing, though.

## Welcome
Workstream: |  | Approved Decision | ICC Decision / Discussion | id (Hide column
Direction Setting Meeting:

## HB
Workstream: |  | Approved Decision | ICC Decision / Discussion | id (Hide column
Direction Setting Meeting: Bed Charge Billing
1 | Three levels of room charges: 1) Ward 2) Semi-Private 3) Private | Approved by group |  | 672
2 | Rules observed by all sites: 1) Every bed is billable (non-OHIP) 2) Only use daily bed charging (not hourly). 3) ICU has a fixed daily rate. 4) Nursery has a nursery daily rate. 5) Same day visits get a one-day charge. 6) We do not charge on day of discharge. 7) Isolation charges - if for medical reasons and not by choice, the patient is not billed the surcharge. | Approved by group |  | 701
3 | Private and semi-private rooms (difference is 1 bed vs 2 beds). Standard price for bed for the hospital. There's a surcharge added for semi-private or private. | Approved by group |  | 702
4 | As soon as patient no longer going back to referring hospital, at midnight they're admitted at referred hospital and need to be discharged at referring hospital. They cannot be registered as inpatients at two hospitals at the same time. | Approved by group |  | 591
5 | Chronic care co-payment that would be paid if patient was in a nursing home. This charge is in addition to the daily rate and is based on the patient's income and there's a maximum daily rate. | Approved by group |  | 589
Direction Setting Meeting: HB Insurance Payment Posting
6 | Self-pay - if payment is made and there are several outstanding accounts for the patient - unless instructions to pay specific account, we post to the oldest account first. | Approved by group |  | 703
Direction Setting Meeting: HB Outstanding Insurance
7 | Charges that are billed to patient only and not insurance: * Medical Appliances | Approved by group |  | 600
Direction Setting Meeting: HB Billing Scenarios
8 | For cosmetic surgery, account is self-pay and prepayment is required in full | Approved by group |  | 709
9 | Interim billing happens last day of the month for all payors | Approved by group |  | 710

## PB
Workstream: |  | Approved Decision | ICC Decision / Discussion | id (Hide column
Direction Setting Meeting: PB Claims and Processing and Reconciliation
1 | Each PB group has their own separate billing offices. | Approved by group |  | 714
Direction Setting Meeting: PB Insurance Payment and posting
2 | TOH uses clearing accounts (Refund/takeback) and so clearing accounts should be used even though ED and UMA both do not use clearnig accounts. | Approved by group |  | 715
Direction Setting Meeting: Charge entry/ charge review
3 | Following go-live, Epic recommends 100% rule-based review for Charge Review, initially. Reduce as confidence in system builds. All agreed | Approved by group |  | 646
Direction Setting Meeting: Charge entry/ charge review
4 | Technical charges are not triggered until the exam is signed/completed by the radiologist. We currently do this, however some physicians are delinquent beyond 6 month (would risk no pmt from OHIP for the tech component). Charges will be dropped upon completion of the exam. | Approved by group |  | 716

## Claims&Remit
Workstream: |  | Approved Decision | ICC Decision / Discussion | id (Hide column
Direction Setting Meeting: HB Claims Processing and reconciliation
1 | Workqueues - to be divided by: HGH: Payor, then inpatient vs outpatient TOH: Payor | Approved by group |  | 594
2 | A workqueue will be created for supervisor review. e.g. If billing officer can't figure out an issue they can manually route to a supervisor WQ | Approved by group |  | 604
3 | Confirmation that OHIP receives claims - a few days after submission to OHIP, a file is available (downloaded) to confirm the number of claims processed etc… Other payors such as RAMQ just sends a 'file was received' confirmation. Everyone including EPIC confirmed that this is good enough for accepting the claim run. | Approved by group |  | 717
Direction Setting Meeting: HB Billing Scenarios Direction (claims and remittance)
4 | Charge information as well as diagnostic and procedure codes required on claim. | Approved by group |  | 718

## HIM
Workstream: |  | Approved Decision | ICC Decision / Discussion
Direction Setting Meeting: Coding Basics
1 | Do you want to use Epic's Coding Workflows | Yes, we will need to get an analyst certified in coding
Direction Setting Meeting: Deficiency Analysis Basics
1 | Do partners want to do Final Analysis? Concurrent Analysis? | • No to Final Analysis (Renfrew wants to do it when a chart is being coded)–TOH may want to do selective service validation once a month using Selective Service Audit tool • All partners want to do Concurrent Analysis
2 | Do you currently, or would you like to use electronic authentication? | All partners currently, or would like to begin using electronic authentication
3 | Is there a Quality Review of Documentation as part of current workflow? | TOH: Would like to use. St. Francis and Hawkesbury currently do it.
Direction Setting Meeting: Release of Information
1 | Do you need ROI faxing? | All partners: YES
2 | Do you want patients to be able to electronically request records? | All partners: YES
3 | For releases, do you want to give access to whole chart or certain parts? | All partners want both partial and whole chart option
4 | Do you bill for releases? Do you outsource releases in any way? Any 3rd party vendors for ROI? | Yes from all (need to harmonize fee schedules); No from all; No from all

## Care Everywhere
Workstream: |  | Approved Decision | ICC Decision / Discussion | id (Hide column
Direction Setting Meeting:

## Cogito
Workstream: |  | Approved Decision | ICC Decision / Discussion | id (Hide column
Direction Setting Meeting:

## Charging
Workstream: |  | Approved Decision | ICC Decision / Discussion | id (Hide column
Direction Setting Meeting: