## Sheet1
# | Date | Milestone | Meeting | Component | Priority | Description of item
1 | Nov 15 2017 | Direction 0 | Emergency Department Arrival and Registraion | ASAP | Risk/Issue | Discussion about who will arrive pt in EPIC. Nurse vs Registration Clerk. TOH policy for the RN to arrive pt. Renfrew and St. Francis use the Registration clerk to arrive a patient. This issue for TOH is that our current process requires that the Clerks follow process for correctly identifying a patient (E.G. FN, LN, DOB OHIP# all need to match before they register a patient) - this item needs follow up with EPIC before it's escalated
2 | Nov 15 2017 | Direction 0 | Emergency Department Arrival and Registraion | ASAP | Risk/Issue | Anonymous patients in EPIC remain anonymous in EPIC until the ED visit is closed - this item needs follow up with EPIC before it's escalated
3 | Nov 15 2017 | Direction 0 | Emergency Physician Overview | ASAP | Risk/Issue | EPIC doesn't allow for the use of Medical Directives for Med students - all orders required verificaiton
4 | Nov 14 2017 | Direction 0 | BORN Reporting | Stork | Risk/Issue | HGH uses an OB documentation tool called MoreOB (OB documention standard guidelines) The Ottawa Hospital stated that many of the standards are reflected in their documentation, but are not based directly off of the MORE OB templates
5 | Nov 15 2017 | Direction 0 | Emergency Physician Overview | ASAP | Risk/Issue | St. Francis MD's expressed that they don't need to assign the ED patients on the Trackboard to themselves or assign them to oncoming MD's
6 | Nov 15 2017 | Direction 0 | ALR and eClaims | Beacon | Risk/Issue | There are currently 5 regional sites delivering chemotherapy. Orders are entered in OPIS at TOH and the regional sites use the TOH instance of OPIS to view the orders and administer. Three of these sites are not part of the Atlas Alliance so we will need to investigate how they will access these orders when Beacon is implemented. The five regional sites are: 1. Hawkesbury 2. Renfrew 3. Cornwall 4. Winchester 5. Pembroke
7 | Nov 16 2017 | Direction 0 | LHIN Diabetes Education | EpicCare Ambulatory | Risk/Issue | The LHIN diabetes education data submission method is different for each site: 1. TOH uploads their data to a LHIN Sharepoint site 2. Hawkesbury submits their data to their LHIN contact via email 3. Renfrew and St Francis submit their data to Pembroke who then compiles it for all Renfew County sites and submits to the LHIN
8 | Nov 15 2017 | Direction 0 | EPIC/TOH Conversation |  | Risk/Issue | Management of Nursing Unit, Clinic stock (floorstock and ADC stock) During the pharmacy tours, Epic expressed concerns regarding the amount of stock not stored in ADC's (on shelves, in locked narcotic boxes, etc.) and regarding the number of stock lists TOH has, many with different med contents. Comment that it could be a resource issue for both build and maintenance
9 | Nov 15 2017 | Direction 0 | EPIC/TOH Conversation |  | Risk/Issue | Pharmacy Inventory Management at HGH currently done in the Pharmacy Information System module within ANZER • Pharmacist from HGH asked what the future state will be, when ANZER is replaced with EPIC
10 | Nov 15 2017 | Direction 0 | EPIC/TOH Conversation |  | Risk/Issue | TOHCC Satellites: During tour today, the Pharmacy Manager mentioned that 3 of the 5 satellite locations for TOHCC are NOT moving to EPIC and Beacon and the impact that may have on chemotherapy ordering, billing, etc. • Satellites in: Renfrew, Hawkesbury, Cornwall, Pembroke and Winchester
11 | Nov 15 2017 | Direction 0 | EPIC/TOH Conversation |  | Risk/Issue | HGH indicated they are completing numerous other pharmacy initiatives, all with delivery timelines prior to, or in line with Epic go live and are currently holding off on some decisions based on what will be required for Epic implementation. i. Pharmacy Renovations ii. Ontario College of Pharmacy visit (Jan 2019) for pharmacy accreditation (HGH on their 'radar' for various reasons, hence the renos) iii. Accreditation Canada visit
12 | Nov 15 2017 | Direction 0 | EPIC/TOH Conversation |  | Risk/Issue | SFMH and RVH both utilize North West TelePharmacy Solutions (3rd party company) to provide medication order entry / verification and clinical pharmacy services; they access the current Pharmacy information but are not employees of those organizations. Not sure what implication that has with Epic. Andrew Wagner (Pharmacy Director at RVH) may contact Project Fusion leadership with some questions. UPDATE: (Nov 22 called with Willow AC/AM) - Shafer indicated that EPIC investigated and as NorthWest is not a software developer, there is not a licensing issue/conflict. Their staff would be able to access Epic; at this point further discussion is required to review that component. - Christel will notify Andrew Wagner (Director for RVH and SFMH) that at this time, he does not need to engage NorthWest or gather information from them, etc.
13 | Nov 15 2017 | Direction 0 | Deficiency Analysis Workflows |  | Risk/Issue | In EPIC all documents, orders, etc… are verified/signed by the provider as should be. This translates to increased number of deficiencies to triage in provider in baskets, for HIM to process, to identify in workflows. How will deficiency/chart completion/will suspension policies be applied?Need to incorporate flagging of deficiencies in coding workflows (RVH, SF, HGH). Risks: Deficiency fatigue may result if too many items flagged as true deficiencies – will need to clearly identify what are legal chart/chart completion/quality deficiencies to ensure safe, quality and compliant deficiency/suspension policy.
14 | Nov 15 2017 | Direction 0 | ROI Basics |  | Risk/Issue | For escalation to ICC: It is the recommendation of the HIM working group/partners/change sponsors to centralize at the Service Area HIM level (each Atlas partner has one centralized area) from the current decentralized processing of ROI requests i.e.: DI, physicians’ offices, clinic settings etc… to the centralized HIM -ROI application of each Service Area within the Facility (Atlas) structure.
15 | Nov 15 2017 | Direction 0 | ROI Basics |  | Risk/Issue | Retention policy for all partners does not including purging – a combination of offsite storage, and various physical locations and systems house the historical charts. From a paper chart retrieval – HIM will need access to all shadow charts, in various areas where they exist. From a historical data retrieval perspective – HIM will need access to scanned documents, microfiche, microfilm data from each partner (service area) and related legacy systems TOH –(HIM-DMI) looking destruction/purging initiatives. Risks: Current HIM ROI resourcing may not be sufficient to handle all requests – may need to redistribute workforce accordingly. Decision/takeaways: ATLAS HIM partners to review and harmonize feestructure, and turnaround times by request types to achieve harmonization across the Atlas platform
16 | Nov 15 2017 | Direction 0 | Legal Medical Records – Releasing PHI |  | Risk/Issue | Workflow within EPIC ROI allows flexibility in deselecting items for release of a Legal Medical Record – organizations to decide on whether the release of information to legal requestors be the same as ROI flow – and not differentiate for Legal Medical record
17 | Nov 15 2017 | Direction 0 | Legal Medical Records (LMR) – Releasing PHI |  | Risk/Issue | Patient Advocacy expressed risk/concern about holding information back for legal medical record release requests. Would recommend not adopting selective practice – Release of legal record should include all documents/components of the chart. Decision takeaways: Leave as per standard ROI processing or Legal Record deselection options, partners in agreement for (confirm next Direction Session) Core documents for release as per request types to be confirmed.
18 | Nov 15 2017 | Direction 0 | Coding Workflows for DAD/NACRS |  |  | NOTE: Concept of episode vs encounter needs to be well understood, episode of care can translated to many encounter(visit register numbers) – matrix has been defined by TOH HIM/Decision Support/IS team – will circulate to integration and HIM teams– many coding applications across partners, HGH, SF, RVH coding modules are included in ANZER ADT, TOH uses WINRECS/METRIQ and imports data from Nephrocare, OPIS for autocoding. Currently – many coding applications across partners, HGH,SF, RVH coding modules are included in Momentum, ANZER ADT, TOH uses WINRECS/METRIQ andimports data from Nephrocare, OPIS for autocoding. Epic note CIHI certified. Do HIM Partners sites continue to code in ANZER? How will this legacy system be supported and integrated to EPIC. Decisions/Takeaways: Data elements required for each abstract category type to be provided to EPIC team by HIM working group.
19 | Nov 16 2017 | Direction 0 | Radiant 360/Cupid Structured Reporting Demo | Radiant/Cupid | Risk/Issue | Cardiac CT/MRI - Division of labour between cardiologists and radiologists
20 | Nov 16 2017 | Direction 0 | Radiant 360 | Radiant | Risk/Issue | WTIS for date-specific exams - Unclear as to whether Epic can support not having wait time calculations start at time of ordering. TOH has the ability to flag date-specific tests so that wait times are not calculated.
21 | Nov 16 2017 | Direction 0 | Radiant 360 | Radiant/Devices | Item to track | Kiosks - Pre-exam questionnaire completion/check-in process for DMI exams - Decision on this needed and an item to be tracked because of financial implications which may drive the process.
22 | Nov 14 2017 | Direction 0 | PACS Consolidation | Radiant | Risk/Issue | 3rd party, remote radiologists at Hawkesbury and the possible implications around training and involvement in the design process
23 | Nov 14 2017 | Direction 0 | PACS Consolidation | Radiant | Risk/Issue | PACS consolidation for Hawkesbury happening at the same time as a new RIS and dictation system. Less of a concern if TOH radiologists end up reading the exams, but more of a concern if remote radiologists in Quebec will be reading.